## Sheet1
Serial Number | Event description | Event Keywords | Pros/Successful tasks | Cons/Recommendations
1 | On Saturday, October 20, 2007, the first of many fires began in Southern California. Driven by strong Santa Ana winds gusting up to 100 miles per hour, the adverse weather conditions in Southern California helped fan a total of 24 fires in seven counties into raging firestorms within a few days. By Sunday afternoon, OES fully activated the Southern Regional Emergency Operation Center (REOC) and the State Operation Center (SOC). | fire, wildfire, firestorm | 1. OES had all of its assigned equipment in Southern California within the first 24 hours. 2. Public-private partnerships were stronger in this emergency than in any prior emergency and were critical in the response. 3. Emergency Management Mutual Aid (EMMA) was used more extensively than in any other disaster. 4. The LACs provided a central place for disaster survivors to talk face-to-face with numerous state and local agency representatives, elected and local officials, and insurance companies. 5. Pairing state regional representatives with federal division supervisors by county worked well in identifying local needs, resolving issues, and keeping the JFO informed. | 1. There was minimal planning and preparedness for sheltering people with disabilities 2. Several state agencies reported a shortage of trained staff, making it difficult to maintain expected staffing levels concurrently 3. Current data management tools, especially the Response Information Management System (RIMS), are inadequate to meet the demands of today’s emergency management needs. 4. There is a need for additional state firefighters to increase staffing of fire engines from three to four firefighters per engine. 5. Transitioning medically fragile/vulnerable populations to alternate facilities/shelters needs improvement. 6. Inability to track emergency resources affected the state’s ability to re-deploy emergency equipment. 7. There is a need for greater federal military coordination to allow for timely deployment of federal military assets during disasters. 8. Enhance SEMS training at all levels of government. 9. A review of the SEMS structure is needed to ensure the integration of disability resources and services into response and recovery activities. 10. Emergency management training, including SEMS/National Incident Management System (NIMS)/Incident Command System (ICS), at all levels of state government needs to be enhanced. 11. Communicate the "leaning forward" approach and philosophy to local government stakeholders. 12. Develop protocols for local, state, and federal interaction with Tribal entities on medicalhealth issues. -A Feasibility Study Report (FSR) is required to document the results of the problem or the opportunity that may be addressed using information technology.-Develop and implement better land use planning and prevention templates, laws, and ordinances to address fire mitigation. -Increase the OES Fire Engine Program by 100 percent.
2 | fires that burned in California during the 2013 fire season where local government proclaimed a local emergency and the Governor proclaimed a State of Emergency. The fires were the Silver Fire, the Powerhouse Fire, the Mountain Fire, the Clover Fire, and the Rim Fire. | fire | 1. Cal OES Inland Region staff provided excellent support to their OAs | 1. Remote locations hampered interoperable communication systems. 2. EOC personnel found difficulty disseminating key information. 3. County departments did not possess a clear understanding of what documentation Federal Emergency Management Agency (FEMA) and Cal OES required. 4. Local officials held misconceptions regarding opening, organizing, and operating a Local Assistance Center (LAC). 5. Local officials mistakenly believed if they waived County Assessor’s fees, the State would reimburse the County for the lost revenue. 6. One OA found their existing Mass Care and Shelter Plan was outdated when the American Red Cross (ARC) required significant county support for shelter feeding operations and logistics during the initial response phase.
4 | The firestorms that occurred in San Diego County beginning at approximately 5:37 p.m. Saturday, October 25, 2003, were the worst in County history and second in damage statewide, only to the East Bay/Oakland Hills Fire in 1991. The day the initial fire started, the temperature in Julian reached 99 degrees Fahrenheit and the humidity was 8%. Santa Ana winds were a major contributing factor to the fire’s unpredictable behavior and rapid progression. On Sunday, October 26th, humidity levels dropped to 7%. These hot, dry winds continued to fan the fire. Flames in excess of 200 feet in height were reported. The fire generated thermal convections which produced extreme erratic fire behavior and made it impossible for firefighters to forecast the fire’s path and spread. | fire, wildfire, high temperature | 1. Public Information via the dissemination of 31 news releases and/or media advisories and regular press briefings; 2. Delivery of resources to the field including medical supplies, heavy equipment, food and water, communications equipment and personnel; 3. Damage Assessment Team activation provided accurate, timely information on damaged and destroyed homes and property; 4. Documentation of ongoing events through numerous Situation Reports and Action Planning; | 1. The importance of providing timely and accurate information to the public was underscored during the activation. 2. Drills/Exercises are invaluable for the proper operation of an EOC during a real event. 3. OES needs to enlist the support of other County staff to represent them in the field at Incident Command Posts to garner more current information. 4. Facility/Infrastructure – the County’s Emergency Operations Center is well equipped with networked computers, but the EOC lacked crisis management software. 5. OES needs to explore more options for alternative EOC sites. 6. Evacuation, sheltering and subsequent claiming of large animals was problematic and at times animal rescue activities placed emergency responders in harm’s way.
5 | Two homemade improvised explosive devices (IEDs) were detonated on Boylston Street in two separate locations near the Finish Line. These explosions took the lives of three spectators: eight-year-old Martin Richard, 29-year-old Krystle Campbell, and 23-year old Lu Lingzi. An additional 264 spectators were injured, many critically.This tragic event initiated a week-long response of the public safety, public health, and medical communities, which culminated in the death of one suspect, and the capture of another. In spite of the malevolence of the perpetrators of these actions, countless extraordinary acts of heroism, bravery and community triumphed. | explosion, injury | 1. Strong Relationships and Successful Unified Command. 2. All-Hazards Medical System for Marathon Day. 3. Well-Planned and Organized Re-Opening of Boylston Street. 4. Activation of a Multi-Agency Coordination Center in Support of Marathon Activities 5. Participation in Multi-Jurisdictional Exercises 6. Formal Mutual Aid Agreements 7. Use of Notification Systems and Tools to Share Information | 1. Lack of Coordination and Management of Mutual Aid within the Watertown Incident. 2. Lack of Weapons Discipline 3. Lack of a Joint Information Center 4. Lack of an Integrated Public Safety Plan for Marathon Day 5. Need for Enhanced Security for the Marathon Course
6 | On August 28, 2011, at 11:00 AM, Tropical Storm Irene made landfall just west of Westport, Connecticut. The Emergency Management Team had been tracking Hurricane Irene the week prior and extensive planning had been put in place. All indications were this hurricane could be the most devastating seen in Connecticut in decades. An extensive public information campaign lead up to the day of the storm utilizing: Press Releases, CodeRed Announcements, News Conferences, and Internet Outlets. | tropical storm,landfall,hurricane,coastal flooding,heavy rainfall | 1. Establishing a Rapid Response Vehicle or 1st Responder RIT was a great idea.-A priority was given to restoring businesses downtown. 2. Purchase of battery operated Smoke/CO detectors to give to residents. 3. Preliminary damage assessment forms distributed in all apparatus prior to the storm were helpful in detailing property damage. 4. Public Information was delivered through numerous means. CodeRed telephone and e-mail messaging, Press releases, Staples FM radio station, Twitter, and various other internet outlets. 5. Providing adequate staffing levels before the storms onset, rather than reacting to an increasing call volume which would cause firefighters to have to travel through the storm to report in. 6. Operating a 2nd or “West Side Command” out of Station 4 worked well. | Rotation of personnel was not always adequate. At time firefighters worked for 18-20 hours straight without a break. Closer tracking and assigning a Resource Leader should be helpful in the future. -Although food was delivered to most stations before the storm, preparation time was not taken into consideration. During the height of activity, rotation through the Senior Center for meals would have been helpful. -Accurate tracking of road closures and wires down between agencies was troublesome at times. A plan for a better mapping system is in the works. -Utilize ICS functions and paperwork. Incident Action Plans were not always completed and shared. Also, establishing formal ICS positions for future incidents would be beneficial. -Utilize ICS functions and paperwork. Incident Action Plans were not always completed and shared. Also, establishing formal ICS positions for future incidents would be beneficial. -Accountability was an issue; implementing a Resource Unit Leader function should be helpful. Also a master handwritten list of personnel was not kept updated in the EOC as in the past. -Use of IP phones in the EOC for Call Taking. This would allow the operator to see the caller’s phone number and the ability to place on hold and transfer a call. -Always assign an Officer or “Director of Communications” to the Dispatch Center during times of high volume. This relieved the dispatcher from continually having to contact the shift commander to make decisions, etc. -Have a computer workstation available for Administrative Assistants in the EOC. This would allow them to keep up on their daily work when assigned to the EOC. A recently installed wireless access point should facilitate this. -Utilize patrol Units or CERT members to free up FD and PD assets on wires down type calls. -Formalization of NIMS/ICS functions. Utilization of ICS forms and assignment of a Resource Unit Leader, Logistics Section Chief, Etc. -Procure additional High Water Vehicles in the future. Utilize a vehicle similar to the PD’s Hummer for the Rapid Response Vehicle. -
9 | On Friday, June 20, 2008, the first of many lightning-caused fires began in drought-stricken northern and central California. Driven by summer storms in the mountainous area of northern and central California, the prolonged drought conditions along with a severe thunderstorm system helped fan over 2000 lightning-caused fires in 26 counties within a few days. By June 21, 2008, OES fully activated the Inland Regional Emergency Operation Center (REOC) and the State Operation Center (SOC) to assist with the coordination of firefighting efforts. Prior to these fires, the Summit Fire in Santa Clara County on May 22, 2008 signaled the beginning of an unusually early 2008 fire season. The large number of fires resulting from this lightning storm was unprecedented especially for such an early fire siege. | lightning,fire,drought, | 1. The “Wildfire Smoke: A Guide to Public Health Officials” has become a national model for public health emergency response to wildfires. 2. The California Department of Socials Services (CDSS) in conjunction with OES deployed Field Onsite Observation Teams (FOOT) consisting of various state agencies’ qualified staff to assist with shelter service assessments and communications opportunities. In addition, there was a well-coordinated volunteer identification and deployment that supported local shelter efforts. 3. The State Emergency Assessment Teams were able to identify emergency protective measures needed that were implemented quickly and effectively. 4. The Local Assistance Centers (LACs) provided a central place for disaster survivors to talk face-to-face with numerous state and local agency representatives, elected and local officials, and insurance companies. 5. There was effective federal military coordination allowing for timely deployment of their military assets during disasters. 6. The CNG, in coordination with the United States Forest Service (USFS), was able to train 2,400 personnel to conduct Type II Hand Crew Operations. 7. The CNG was able to establish the Military Resource Advisory Group (MRAG) at the SOC to support the State Incident Command System. 8. The CALMAC was able to make effective use of the Emergency Management Assistance Compact (EMAC) to obtain assistance from numerous states that would often have resources available to respond quickly in meeting California’s firefighting needs | 1. Additional staffing and training at state, local, and regional levels. Additional fire fighting resources. 2. Additional funding for emergency response operations. 3. Enhanced data and information management tools. 4. Enhanced data and information management tools. 5. Better pre-positioning of state resources for fire suppression and evacuation and sheltering operations. 6. Improved regional Emergency Operations Center (EOC) facility conditions. 7. There is a need for advance planning related to identifying trained personnel, including volunteers, supplies and alternate locations for sheltering pets and their owners at the same site.8. State resources were deployed in a “leaning forward” strategy that at times caused confusion at the local level. This was especially true of the Field Onsite Observation Team (FOOT) personnel. The FOOT members were deployed very quickly to assess whether the needs of populations with access and functional needs were being met in local shelters, but local governments were not aware of their deployment.9. CNG needs to continue to work with the US Military to enhance communication and coordinate assets in response to emergencies. 10. Develop and implement better land use planning and prevention templates, laws, and ordinances to address fire mitigation.11. Preliminary Disaster Assessments (PDAs) should be attempted when it is actually safe to do so and when the damage sites can really be visited. This will prevent over or under reported estimates.
11 | During the afternoon hours of August 18, 2005 a rapid developing severe storm moved through the area. The National Weather Service issued a Tornado Warning for the County of Dane at 5:21 p.m. The storm was monitored from the 911 Center and Dane County Emergency Management. Amateur radio personnel were utilized in the Emergency Management communication room to collect information from spotters in the field. Several funnel clouds were spotted throughout the Dane County area. At approximately 6:15 p.m. a F3-F4 tornado, as defined by the National Weather Service, touched down in the Town of Dunn. Its 17 mile track of devastation affected the Towns of Dunn, Pleasant Springs, Christiana, Albion, Dunkirk and the City of Stoughton leaving 69 homes destroyed, 84 homes with major damage and 220 received minor damage or were classified as affected. | tornado, storm, | 1. The EOC was activated immediately following the 911 Center communiqué that a tornado was on the ground in the Stoughton area and they were receiving reports of damage. 2. Internal EOC contact sheets worked well. 3. Meetings with affected jurisdictions was appreciated and effective but need to be a brief and to the point. The meeting conducted with affected residents was beneficial and should be considered in the future. 4. Damage assessment for the most part went very well. 5. Consensus was that resource allocation, support and response was excellent. The EOC supported requests affectively. State and local resources were utilized. Rock and Green Counties provided additional emergency lighting | A system of tracking displaced persons is needed. - An electronic system of tracking donated goods, services, and contributions is needed. - There is a need for a formal Long Term Recovery Plan. - Additional training is required with all personnel on the role of the Emergency Operations Center (EOC). - There is a need to create maps of town, cities and villages to be transported in the mobile command center. - Access to the scene was difficult to control. - Need to refine systems to enhance interoperability and communications to minimize self-assignment, and duplication of response and recovery efforts.
12 | In the summer of 2014 numerous wildfires started as a result of lightning strikes throughout the Central Washington area. The largest and most complex was the Carlton Complex Fire which started on July 14 | wildfire, lightning | 1. Federal state and local jurisdiction working out of the same facility, having FEMA ETART resource available,Having extra USFS staff with BAER experience, Having state/private BAER team collaborated with the BAER team, Use of GIS Collector application, Having GIS Personnel pre-deploy, | 1. Make sure both agencies and individuals are familiar with what ETART was doing in the past mission, 2. more time to train up with soil science SMEs, 3. Having more non-SME staff / helpers, 4. More time for soil analysis, pre-deploy sooner, 5. secure IT technology solutions, 6. set up MAA or MOU before disaster strikes
13 | From September 8 through 16, 2013, the Boulder region experienced unprecedented rainfall that caused significant flooding, loss of life and widespread damage. As a result of the flooding, Boulder County (including the City of Boulder) was designated a “Major Disaster” by the Federal Emergency Management Agency (FEMA)1. This event was caused by a 1,000-year rainfall, which brought up to 16 inches of rain to Boulder in eight days. In addition, the rainfall caused 25- to 100-year flooding along all 15 major creeks and the 23 irrigation ditches, which had overwhelmed the city’s storm drainage and sanitary sewer systems. Additional information, including analysis of the flooding by creek, | flood, rainfall | 1. Staff came together with the common mindset to be supportive and understanding for the community during this time of need. Regardless of their daily job duties representatives from all city departments supported one another in the recovery efforts. This was most evident in the immediate surge to help with debris clean-up operations. 2. Establishing the flood recovery team was essential to the success of the community. The ever-changing dynamics of the flood recovery, coupled with the increased need to break down pre-existing departmental silos, required a new coordination structure. Hiring dedicated staff and bringing together cross-departmental teams proved valuable in supporting recovery operations. Forming a team and assigning tasks with the culture and values of the city in mind allowed this group to succeed. 3. Water and wastewater service remained operational. The city’s water treatment and wastewater treatment systems remained operational throughout the flood, although sewer backups impacted hundreds of homes and localized areas temporarily lost service. Dedicated and empowered staff worked hard to ensure the continued functionality of the water and wastewater systems during and after the flood. | 1. Help people get assistance. Facilitate access to individual assistance for affected homeowners, renters and businesses to support their recovery from flood impacts and strengthen long-term resilience. 2. Restore and enhance our infrastructure. Invest in projects to restore services and to rebuild and enhance infrastructure, as appropriate, in the interests of public health and safety, community quality of life, and long-term resilience. 3. Assist business recovery. Work with the Boulder business community and key partners to connect affected businesses with resources, recover quickly from flood impacts, and support long-term economic vitality. 4. Pursue and focus resources to support recovery efforts. Work in partnership with volunteers, governmental and other agencies to maximize financial resources and efficiencies for recovery. 5. Learn together and plan for the future. Engage the Boulder community in assessing neighborhood impacts, refining and rethinking community design options, prioritizing actions and opportunities that mitigate hazards before rebuilding and support long-term community resilience and sustainability. In doing so, we build a city both greater and more beautiful than we were before.
14 | At 1000 hours a rupture occurs on the southern segment of the San Andreas occurs, generating a magnitude 7.8 Southern California earthquake (similar to the recent earthquake in China) impacts the region, causing loss of lives and massive damage to infrastructure, including critical transportation, power, and water systems. The strongest shaking and greatest damage is near the stretch of the San Andreas Fault that extends through the fastest growing areas of Southern California, including the Coachella Valley, Inland Empire and Antelope Valley. It takes a little over two minutes before the shaking is felt in the Greater Los Angeles area. At least 10 million people are exposed to heavy shaking. California's efforts at mitigation have concentrated on life safety and have been largely successful. Thus, in spite of the large numbers of people in highly shaken areas, initial estimates place the death toll at only about 1,800 fatalities. Early estimates are 55,000 injured. Initial estimates of displaced people in the region is 500,000, with nearly half of those (247,000) representing people in the jurisdiction of our Chapter. | earthquake, | 1. Exercise contained real life scenarios that were beneficial in role playing. 2. Participants found the hands on experience highly beneficial. 3. Participants enjoyed the interaction, teamwork and meeting other volunteers. 4. Open communication between groups that worked at same site. 5. Number of individuals using unknown acronyms | 1. Utilize outside volunteers to act as clients. 2. Outline all job activities and roles with descriptions for participants. 3. Be willing to say no when appropriate or not able to satisfy request. 4. Utilize resources to fix problems. 5. Develop scenarios that allow shelter workers to problem solve without directly going to shelter manager. 6. Do not give out information when unsure of validity. 7. More participants to experience shift change and More role playing of client worker interface
15 | The Highway 31 Fire far exceeded the impact of the other 2,001 wildfires the Forestry Commission responded to during the 2009 wildfire season and was easily the largest wildfire since 1976. The $50 million in damage was the greatest of any past wildfire. Its impact was only surpassed by past wildfires that claimed the lives of firefighters and citizens. The fire response involved agency personnel from every part of the state, either on the fireline or providing valuable support to the firefighting effort. The extreme fire behavior, inaccessibility, and complexity of the Highway 31 Fire made it very difficult to control and put the lives of citizens, firefighters, and other first responders in great jeopardy. Within a few hours, what started as a small woods fire became the worst wildfire in South Carolina’s history. Highly volatile, continuous fuels, dry weather, strong winds, and unusual weather events combined to create a powerful force of nature that was unpredictable, resulting in 76 homes destroyed, 97 homes damaged, destruction of many other structures and vehicles, plus much business lost by the surrounding community. The home owners lost heirlooms, important documents, family photos, and other belongings, but thankfully, no loss of life or serious injuries occurred. | Wildfires Damage Firefighting Extreme Inaccessibility Worst Destroyed Weather Unpredictable Injuries | 1. Firefighters were able to fight fire aggressively, but provided for safety first. 2. The initial attack IC was very familiar with the area, the fuel types, and the past history of large fires. This knowledge, commbined with his experience, allowed the IC to make excellent decisions during the first few hours of this incident. 3. The Duty Officer at SCFC headquarters and the Incident Commander for the IMT worked to contact team members and coordinate the IMT deployment. 4. Incident Command System (ICS) structure was increased in scale as the incident developed. | 1. Interoperable communication with other responding agencies is crucial. 2. Annual exercises should be conducted in Horry County and other counties in the state where the potential for large fires exists. 3. The Forestry Commission should continue the development of qualified incident management teams. 4. In the future, a lack of equipment replacement funding, the loss of experienced personnel due to budget reductions, and the difficulties in recruiting and retaining qualified personnel could have serious impacts on the agency’s response capability.
17 | On January 6, 2014 the heat exchangers in the Public Health Laboratory building went down between 3:00 and 4:00 AM during a night when temperatures across Minnesota were extremely cold. The alarm system in the building did not activate. There was significant damage to the heating system. As a result, the water in the radiator pipes in the building froze. The situation was discovered after 7:00 AM and the heat was reinstated; however, many pipes were damaged and began leaking water. Staff responded by moving equipment and using tarps to cover equipment. The infectious disease lab, environmental lab and the newborn screening lab were most significantly affected. Areas of the lab had standing water and were not habitable so many staff were sent home on emergency leave granted by Minnesota Management and Budget (MMB). | Heat Extemely Cold Alarm Froze Damaged Leaking Emergency | 1.Pre-identified staff were available and either physically present or were connected by their Blackberries. 2. Most of the required staff had previously received ICS training and had participated in exercises. | 1. Primary communication in the Public Health Laboratory uses the computer system which was not operable during this incident requiring direct face to face communication to some of the staff to notify and request to assemble in the lobby. 2. A sign-in sheet was not completed to record the attendance; however, the Documentation person recorded the attendees in her meeting minutes.
18 | During the spring and summer of 2010, the Northwestern Division (NWD) experienced extensive flooding in the Missouri River Basin and its tributaries resulting in emergency declarations in two NWD districts, Omaha and Kansas City. Starting with January ice jams on the Missouri River, ground saturation from 2009, and significant snowpack on the plains, Omaha District’s technical assistance in January moved to advance flood preparations and flood fight activities by March. With extensive and heavy spring rains, and delayed snowmelts, flood activity swelled again for Omaha District extending from May into August, with the most hectic pace in late June/early July. For Kansas City District, the same extensive spring rainfalls instigated initial flood fight assistance in May, which broadened and continued through August. In both late June and July, flood fights elevated in communities along tributaries both up and downstream of Kansas City. | flooding, snowmelt, heavy spring rains, floodflight, | 1. Less damages occurred because of the flood fight. 2. Daily conference calls worked well. 3. Corps did great in a very challenging job 2) Reservoir Control 4. Good Job / no concerns received 3) Coordination Calls / Info sharing worked well 5. Prep / Early effort prep E.T. Support (AM) helpful 6. Work flood solutions (Get studies done) 7. Good positive feedback | 1. Corps Needs to step up rehab. 2. Water Management office personnel need to see flooding first hand 3. FEMA certification program is a concern (confusion) 4. Drainage ditches are still a concern for fall harvest (still water filled) 5. Crop Losses / reduced yield 6. Security was a problem 7.Advance Measures are very important
19 | DRILL: A pilot of a DC-9 reported to the tower there was smoke in the cockpit, the aircraft was 10 minutes out with 5,000 pounds of fuel and 95 SOB’s. During approach to runway 15 the pilot aborted the landing and crashed on Taxi Lane “Mike”. Debris struck vehicles outside the fence line complicating the incident with one bus fire, (2) cars requiring extrication of passengers and (1) bus on its side requiring extrication of passengers. The drill area was set-up with a DC-9 aircraft located on Taxi Lane “Mike” with 95 passengers moulaged to simulate various injuries. A bus fire in the open field, (2) cars and a bus turned over and outfitted with mannequins to simulate fire and extrication functions. | smoke, debris, bus fire, fire | 1. “Airport Emergency Plan” has the resources to handle all Airport emergencies. | 1. Radio communications for Bradley Airport Fire Department and mutual 2. aid departments responding to the Airport should be reviewed by communication experts to correct radio traffic issues that were observed during the drill. 3. EMS coverage for mass casualty incident requires special training that addresses limited resources with a high number of patients. 4. The need exist for the Airport Authority to provide a designated gathering area in the Terminal complex for families and Airline representatives. 5. There is some confusion as to who makes the initial notification to the Red Cross. 6. Feedback from the debrief identifies a need for more Airline, Red Cross and Airport staff training on the Airport family assistance program.
20 | Chevron Fire: On the evening of Monday, August 6, 2012, at 18:37 hours, a major fire erupted in the Number 4 Crude Unit at the Chevron Richmond Refinery where workers had been attempting to repair a small hydrocarbon leak. Fortunately, workers had been evacuated a few minutes before the fire erupted, and there were no serious casualties on the scene. A Level 3 Community Warning System (CWS) notification was activated, sounding sirens warning persons in nearby areas to go indoors and shelter-in-place (SIP). A SIP order was then issued by the County Health Officer covering the cities of Richmond and San Pablo and the community of North Richmond. That SIP remained in effect until 23:12, about four and a half hours. Weather conditions were such that most of the smoke rose quite high and drifted northeastward toward Martinez, where some odors were detected by County Hazardous Materials’ crews. | Wildfire Firestorm Fire | 1. staff came together with the common mindset to be supportive and understanding for the community during this time of need. 2. Regardless of their daily job duties representatives from all city departments supported one another in the recovery efforts. | 1. Escalation of the MCI from Tier 0 to Tier 3 by the EMS Operations Center, while intuitive, required and consistent with the MCI Plan in this unusual and rapidly evolving situation, was delayed. 2. Both the MCI Plan and the Health Services Medical Surge Plan should be reviewed and revised, if appropriate, in consideration of incidents resulting in a similar surge in 9-1-1 responses and/or significant impact on hospital resources in one area of the county.
22 | Salmonella Typhimurium: November 10, 2008 salmonella typhimurium peanut-related outbreak in 46 states and Canada over a four month period. A total of 691 cases and 9 deaths were reported during the response. The outbreak monitoring returned to baseline levels on March 17, 2009, the heightened response by the CDC was 127 days long. | outbreak, | 1. Early Coordination with Federal External Partners. 2. Creative Communication Strategies . 3. Full integration of multiple CDC Organizations into the Investigative Processes. | 1. Greater Evaluation of Ingredient-Based Outbreak Challenges . 2. New Strategies for Strengthening the Timeliness of Interviewing, Testing, and Analysis . 3. Further Improvement of the Messaging Clearance Process .
23 | On the evening of October 29, 2012, Sandy made landfall in southern New Jersey. Sandy was the second-largest Atlantic storm on record, with effects felt across 24 states. The storm battered the East Coast, particularly the densely populated New York, New Jersey, and Connecticut region, with heavy rain, strong winds, and record storm surges, and with heavy snowfall in West Virginia and the Appalachian Mountains. In Sandy’s immediate aftermath, over 23,000 people sought refuge in temporary shelters, and over 8.5 million customers were left without power. The storm flooded numerous roads and tunnels and blocked transportation corridors, contributing to fuel shortages across the New York metropolitan area. Ultimately, the storm caused tens of billions of dollars in damages, damaged or destroyed hundreds of thousands of homes, and killed at least 162 people in the United States. | atlantic storm, storm, landfall,heavy rain,storm surge, strong winds, flooding | 1. Using an online crisis management system to coordinate Federal response operations 2. Integrating response and recovery efforts with nongovernmental partners 3. Completing one of the largest and most diverse personnel deployments in FEMA history | 1. Integrating Federal senior leader coordination and communications into response and recovery operations. 2. Coordinating Emergency Support Functions (ESFs) and Recovery Support Functions (RSFs) to support disaster response and recovery. 3. Implementing incident management structures 4.Using planning and analysis to drive operational decision-making . 5. Ensuring continuous improvement of disaster doctrine, policies, and plans. 6. Reducing the complexity of the Public Assistance program. 7.Coordinating among states, localities, and tribes . 8.Ensuring a qualified disaster workforce 9. Mobilizing the FEMA workforce for disaster response 10. Supporting deployed personnel 11. Ensuring continuity of operations
24 | Hurricane Matthew ravaged the coastal communities of the State. Hurricane Matthew made landfall near McClellanville, a small fishing community in Charleston County, as a category one hurricane on October 8, 2016. Neighborhoods were left in ruins as the storm cut a path of destruction through South Carolina. A large portion of South Carolina was under a State of Emergency for the second time in as many years. Wind damage from the storm demolished homes across the coastal counties of the State. Entire neighborhoods were underwater over forty miles inland. 833,000 homes were without electricity. 400,000 people evacuated from their homes in advance of the storm. Despite this, four South Carolina residents lost their lives. Hundreds more lost their homes. | Hurricane, landfall, storm, wind damage | 1. Utilizing empirically based measures of community social vulnerability provided an “apolitical” approach for distributing scarce disaster recovery dollars and rebuilding resources for the most benefit to the places that were worst impacted and least able to bounce back on their own from this disaster. | 1. The Hazard Mitigation Grant Program (HMGP) may be a critical part of long-term resilience improvements for infrastructure in the impacted area.
25 | This After-Action Report (AAR) describes the activities of Arlington County and the supporting jurisdictions, government agencies, and other organizations in response to the September 11, 2001, terrorist attack on the Pentagon. This incident produced a unique paradigm of response considerations and requirements. It was a major fire and rescue operation within the broader context of a terrorist attack. This terrorist attack occurred in Arlington County, VA, but at a U.S. military facility under the direct control of the Secretary of Defense. The incident response engaged a large number of agencies, organizations, and individuals from all levels of government and the private sector, and it lasted for an extended period. | Terrorist Fire Rescue Attack | 1. The primary response participants understood the ICS, implemented it effectively, and complied with its provisions. 2. The management and integration of mutual-aid assets and the coordination and cooperation of agencies at all government echelons, volunteer organizations, and private businesses were outstanding. 3. The CEMP proved to be what its title implies. It was well thought out, properly maintained, frequently practiced, and effectively implemented. 4. At the time of the Pentagon attack, Arlington County already had in place an aggressive, well-established EAP offering critical incident stress management (CISM) services to public safety and other county employees. 5. The ACFD has long recognized the possibility of a weapons of mass destruction (WMD) terrorist attack in the Washington Metropolitan Area and has pursued an aggressive preparedness program for such an event, including its pioneering work associated with the MMRS. | 1. Organizations, response units, and individuals proceeding on their own initiative directly to an incident site, without the knowledge and permission of the host jurisdiction and the Incident Commander, complicate the exercise of command, increase the risks faced by bonafide responders, and exacerbate the challenge of accountability. 2. Arlington County does not have a facility specifically designed and equipped to support the emergency management functions specified in the CEMP. 3. Almost all aspects of communications continue to be problematic, from initial notification to tactical operations. 4. Arlington County, like most other jurisdictions, was not logistically prepared for an operation of the duration and magnitude of the Pentagon attack. 5. Communications and coordination were deficient between EMS control at the incident site and area hospitals receiving injured victims.
26 | In late August, Isaac was named the ninth storm of the 2012 Atlantic Hurricane Season. Hurricane Isaac struck parts of Florida as a Tropical Storm before heading west toward Louisiana. Heavy rainfall from Isaac spread up the Florida coast. On August 27, a tornado touched down in Indian River County for about two minutes, damaging 95 houses. | Tropical storm, tornado, storm | 1. The ESF8 Incident Management Team (IMT) was established efficiently, staffed appropriately, and was able to produce the initial Incident Action Plan within 24 hours of activation. 2. Thorough advanced planning was conducted to address the needs of the delegates and visitors in the Tampa area and the concurrent potential for dual impact to the State in response to both the RNC and a hurricane. ESF8 was able to put this planning to use when threatened by Tropical Storm Isaac. An Incident Command System (ICS) complex structure was used to manage the RNC and Tropical Storm Isaac simultaneously. 3. The process for conducting healthcare facility status verification was improved from the process used during Tropical Storm Debby earlier in 2012. | 1. The process for reporting County Health Department open/closed status was not consistent or efficient. This deficiency was also noted in the Tropical Storm Debby After-Action Review. 2. The process for reporting special needs shelter census information was inconsistent. 3. “Dual populations” of Functional Needs Support Services (FNSS) and special needs shelter (SpNS) designations continues to cause confusion.